## Slide 1
Welcome to
Unit 8 Part 15
MATH366 Probability and Statistics
https://online.stanford.edu/sites/default/files/styles/figure_default/public/2018-04/theory-of-probability_stats116.jpg?itok=ms4fRMO-

## Slide 2: What’s Up?
Today we will be going over:
Review: Uses for discrete probabilities New: Project Management Charts

## Slide 3: What’s Up?
Outcome 3) Modeling will be assisted by Monte Carlo simulations run with mathematical software
Outcome 4) Calculate the parameters of several discrete random variable distributions and compute the probability of events in a typical discrete event application

## Slide 4: Review
http://995642590.r.lightningbase-cdn.com/wp-content/uploads/2010/12/looking-back-hrexaminer-v144-cover425px.jpg

## Slide 5: Assignment
Sometimes you need to make decisions about assigning people to jobs, tasks to machines, etc.
These are called “Assignment Problems”

## Slide 6: Assignment
Again, you want to minimize something: cost, time takes, errors made, maintenance required
or maximize something: profits, number of customers, etc.

## Slide 7: Assignment
Suppose past experience has given you information on how much it would cost for each of n employees to do each of k projects
VFrench, 2022

## Slide 8: Assignment
How many ways can you assign the projects to the employees?

## Slide 9: Assignment
There are
n!
ways you can assign the projects
VFrench, 2022

## Slide 10: Assignment
Once you know how many possible ways there are to make the assignments, we need to list those possibilities:
VFrench, 2022

## Slide 11: Assignment
Once you have the list of possible assignments, you need to list the cost of each employee doing the assigned task
VFrench, 2022

## Slide 12: Assignment
Calculate the total costs for each assignment and identify the assignment with the lowest cost:
VFrench, 2022

## Slide 13: Probability Assignment
Some Assignment problems are about time
Some are about cost or profit
Some are about probabilities

## Slide 14: Probability Assignment
Probability is the likelihood of a favorable outcome
It is designated “P”

## Slide 15: Probability Assignment
# favorable outcomes
total # of outcomes
So, you have to be able to count the number of favorable outcomes and the total number of outcomes
P =

## Slide 16: Probability Assignment
Probabilities are most often expressed in terms of %

## Slide 17: Probability Assignment
Because the number of favorable outcomes is always less than the total number of outcomes
0% ≤ P ≤ 100%

## Slide 18: Probability Assignment
Multiplication rule - if you have sequential outcomes:
P(one occurring, then another occurring) =
P(one occurring)*P(another occurring)

## Slide 19: Probability Assignment
When we had Assignment problems trying to minimize time or cost we had to add the values to get the total time or cost

## Slide 20: Probability Assignment
When we have a problem with probabilities, we will have to multiply the probabilities to get the total probability

## Slide 21: Questions?
http://i.imgur.com/aliTlT3.jpg

## Slide 22: Project Management
… is planning, organizing, motivating, and controlling resources to achieve specific goals

## Slide 23: Project Management
A project is a temporary endeavor with a defined beginning and end

## Slide 24: Project Management
Usually projects are time-constrained and are often also constrained by funding or deliverables

## Slide 25: Project Management
Managing projects is very ancient
http://1.bp.blogspot.com/-b9AWEon9HSk/UDU_kZCaatI/AAAAAAAAB-g/w9KKYs1TPjg/s200/pyramid-building3.jpg

## Slide 26: Project Management
One of the founders of Project Management is Henry Gantt
(May 20, 1861 –
November 23, 1919)
He was an
American
mechanical engineer
and management
consultant
https://alamy-ltd.ewrvdi.net/c/77643/748811/10905?u=https%3A%2F%2F
www.alamy.com%2Fstock-photo-henri-Gantt-139984479.html

## Slide 27: Project Management
He is famous for inventing the Gantt chart

## Slide 28: Project Management
Gantt chart:
http://www.monkeybreadsoftware.de/realbasic/chartdirector/images/colorgantt_m.png

## Slide 29: Project Management
Gantt charts show the viewer when parts of the project are to be done and how long each will take
http://www.monkeybreadsoftware.de/realbasic/chartdirector/images/colorgantt_m.png

## Slide 30: Project Management
A different way of graphing project timing is the “Critical Path Method” (CPM)
http://www.ahds.ac.uk/images/exec/project-management-illustration1.gif

## Slide 31: Project Management
CPM includes paths showing which activities must be done before the next activity can start
http://www.ahds.ac.uk/images/exec/project-management-illustration1.gif

## Slide 32: Project Management
Times are shown using numbers, not lengths of bars
http://www.ahds.ac.uk/images/exec/project-management-illustration1.gif

## Slide 33: Project Management
Another way of graphing project timing is the “Program Evaluation and Review Technique” (PERT)
http://www1bpt.bridgeport.edu/sed/projects/cs597/unfiled/zhipingli/Pert.gif

## Slide 34: Project Management
CPM uses only a single estimate of the duration of each activity
PERT uses up to three estimates of the duration of each activity (optimistic, likely and pessimistic times)

## Slide 35: Project Management
This PERT chart uses how many activity duration times?
http://www1bpt.bridgeport.edu/sed/projects/cs597/unfiled/zhipingli/Pert.gif

## Slide 36: Project Management
Another ‘nother way of graphing project timing is the “Activity on Node” (AON) chart
http://project-management-basics.com/images/project%20management/big/
AON_network_bubble.png

## Slide 37: Project Management
Each type of chart provides more information but is harder to read and understand

## Slide 38: Questions?
http://i.imgur.com/aliTlT3.jpg

## Slide 39: Project Management
Most of the charts you will do for your boss are Gantt charts
They are easy to do in Microsoft Project but can also be done in Excel

## Slide 40: Project Management
Suppose you have a project you want to chart
It has 7 activities (A-G)

## Slide 41: Project Management
You know approximately how long each activity will take to complete
You know which activities need to be done before the next can begin (“immediate predecessors”)

## Slide 42: Project Management
Make a table summarizing your information:
Activity | Expected Time (weeks) | Immediate Predecessors
A | 2 | -
B | 3 | -
C | 5 | A
D | 6 | B
E | 1 | C,D
F | 4 | D
G | 2 | E
VFrench, 2022

## Slide 43: Project Management
Start with a title and your list of activities
VFrench, 2022

## Slide 44: Project Management
Add a few time intervals (you’ll probably need more…)
VFrench, 2022

## Slide 45: Project Management
Activity A is expected to last two weeks
Activity | Expected Time (weeks) | Immediate Predecessors
A | 2 | -
B | 3 | -
C | 5 | A
D | 6 | B
E | 1 | C,D
F | 4 | D
G | 2 | E
VFrench, 2022

## Slide 46: Project Management
Highlight a two-week area next to Activity A
VFrench, 2022

## Slide 47: Project Management
Click the “Fill” icon:
VFrench, 2022

## Slide 48: Project Management
Pick a color you like:
VFrench, 2022

## Slide 49: Project Management
Activity B is expected to take 3 weeks
Activity | Expected Time (weeks) | Immediate Predecessors
A | 2 | -
B | 3 | -
C | 5 | A
D | 6 | B
E | 1 | C,D
F | 4 | D
G | 2 | E
VFrench, 2022

## Slide 50: Project Management
It doesn’t have any predecessors, so it could start at the same time as Activity A
Activity | Expected Time (weeks) | Immediate Predecessors
A | 2 | -
B | 3 | -
C | 5 | A
D | 6 | B
E | 1 | C,D
F | 4 | D
G | 2 | E
VFrench, 2022

## Slide 51: Project Management
Select the cells:
VFrench, 2022

## Slide 52: Project Management
Select the same or a new color:
VFrench, 2022

## Slide 53: Project Management
Activity C is expected to take 5 weeks
Activity | Expected Time (weeks) | Immediate Predecessors
A | 2 | -
B | 3 | -
C | 5 | A
D | 6 | B
E | 1 | C,D
F | 4 | D
G | 2 | E
VFrench, 2022

## Slide 54: Project Management
It has a predecessor, though!
Activity A must be completed before it can start!
Activity | Expected Time (weeks) | Immediate Predecessors
A | 2 | -
B | 3 | -
C | 5 | A
D | 6 | B
E | 1 | C,D
F | 4 | D
G | 2 | E
VFrench, 2022

## Slide 55: Project Management
Activity A ends on week 2, so start Activity C’s cells then
VFrench, 2022

## Slide 56: Project Management
Pick another color (or use the same one!)
VFrench, 2022

## Slide 57: Project Management
Activity D takes 6 weeks and starts after B is done
Activity | Expected Time (weeks) | Immediate Predecessors
A | 2 | -
B | 3 | -
C | 5 | A
D | 6 | B
E | 1 | C,D
F | 4 | D
G | 2 | E
VFrench, 2022

## Slide 58: Project Management
VFrench, 2022

## Slide 59: Project Management
Activity E takes 1 week and starts after both C and D are done
Activity | Expected Time (weeks) | Immediate Predecessors
A | 2 | -
B | 3 | -
C | 5 | A
D | 6 | B
E | 1 | C,D
F | 4 | D
G | 2 | E
VFrench, 2022

## Slide 60: Project Management
VFrench, 2022

## Slide 61: Project Management
Activity F takes 4 weeks and starts after D is done
Activity | Expected Time (weeks) | Immediate Predecessors
A | 2 | -
B | 3 | -
C | 5 | A
D | 6 | B
E | 1 | C,D
F | 4 | D
G | 2 | E
VFrench, 2022

## Slide 62: Project Management
VFrench, 2022

## Slide 63: Project Management
Activity G takes 2 weeks and starts after E is done
Activity | Expected Time (weeks) | Immediate Predecessors
A | 2 | -
B | 3 | -
C | 5 | A
D | 6 | B
E | 1 | C,D
F | 4 | D
G | 2 | E
VFrench, 2022

## Slide 64: Project Management
The complete chart:
VFrench, 2022

## Slide 65: Project Management
If you used all the same color:
VFrench, 2022

## Slide 66: Project Management
You will probably want to outline each bar:
VFrench, 2022

## Slide 67: Project Management
Tah-dah!
VFrench, 2022

## Slide 68: Project Management
How long will the project take?
VFrench, 2022

## Slide 69: Project Management
What is the last activity completed?
VFrench, 2022

## Slide 70: Project Management
If the colors mean something, be sure to label them!
VFrench, 2022

## Slide 71: Questions?
http://i.imgur.com/aliTlT3.jpg

## Slide 72: Project Management
Try the second Gantt chart on your own!

## Slide 73
Questions?
http://i.imgur.com/aliTlT3.jpg

## Slide 74: Summary
Today we studied:
Review of uses for discrete probabilities
Project Management Charts

## Slide 75: You Survived!
www.playbuzz.com